WEEK 1: Project Review and Development Planning

INTENDED LEARNING OUTCOME

At the end of this activity, students should be able to:

Develop a comprehensive project implementation plan by reviewing the approved capstone proposal, validating project scope, incorporating panel recommendations, assigning project responsibilities, preparing a project schedule, and establishing project monitoring tools.

OVERVIEW OF WEEK 1 OUTPUTS

By the end of Week 1, each group must submit:

- Panel Recommendation Compliance Matrix

- Project Scope Validation Form

- Work Breakdown Structure (WBS)

- Revised Gantt Chart

- Project Development Plan

- Repository Setup Report

- Adviser Consultation Record

ACTIVITY 1

Review of Panel Recommendations

Purpose

To ensure that all recommendations from the proposal defense have been reviewed and addressed before implementation begins.

Procedure

- Secure a copy of the proposal defense evaluation sheet.

- Review all comments from the panel.

- Discuss as a group how each recommendation will be addressed.

- Complete Form 1.

FORM 1

PANEL RECOMMENDATION COMPLIANCE MATRIX

Instructions

For every recommendation:

- Copy the recommendation exactly as stated by the panel.

- Describe the action that the group will take.

- Identify supporting evidence.

- Mark the status.

| No. | Panel Recommendation | Planned Action | Evidence | Status |
| --- | --- | --- | --- | --- |
| 1 | Add quantitative data to strengthen the project justification. | Review and update Chapter 1 by incorporating actual statistics, observed attendance data, queue length, and manual attendance duration gathered from the client. | Revised Chapter 1 – Project Context | Completed |
| 2 | Convert the Statement of the Problem into measurable research questions. | Revise the Statement of the Problem into interrogative form and align each question with measurable variables and evaluation metrics. | Revised Chapter 1 – Statement of the Problem | Completed |
| 3 | Align the project objectives with measurable outputs and evaluation criteria. | Refine the project objectives to include measurable indicators such as processing time, attendance accuracy, queue reduction, and security evaluation. | Revised Chapter 1 – Objectives | Completed |
| 4 | Clarify the project's scope and limitations. | Update the Scope and Limitations by specifying LAN deployment, prototype limitations, excluded system features, and hardware constraints. | Revised Chapter 1 – Scope and Limitations | Completed |
| 5 | Improve the organization of the literature review. | Reorganize Chapter 2 using thematic sections including IoT Attendance Systems, RFID Technology, Biometric Authentication, Network Security, and Multi-Layer Security Frameworks. | Revised Chapter 2 | Completed |
| 6 | Clearly identify the research gaps addressed by the study. | Revise the literature synthesis to emphasize the lack of teacher authentication, multi-layer security, and classroom-level attendance validation in existing systems. | Revised Chapter 2 – Synthesis | Completed |
| 7 | Remove ambiguity in the research methodology. | Refine Chapter 3 by clearly explaining the Design and Development Research approach supported by Experimental and Survey Research methods. | Revised Chapter 3 – Research Design | Completed |
| 8 | Ensure all evaluation metrics are measurable. | Add instrument-to-metric mapping tables, evaluation criteria, success indicators, and mathematical formulas for system performance measurement. | Revised Chapter 3 | Completed |
| 9 | Justify the respondents and sampling technique. | Explain the purposive sampling method and justify the selection of students, teachers, administrators, and the IT administrator. | Revised Chapter 3 – Participants | Completed |
| 10 | Include measurable comparison variables for system evaluation. | Introduce performance formulas for processing time, efficiency, waiting time, queue length, and attendance accuracy. | Revised Chapter 3 – Experimental Design | Completed |
| 11 | Strengthen the system's security evaluation. | Integrate security testing using Wireshark, Nmap, and Metasploit in a controlled LAN environment together with vulnerability assessment criteria. | Revised Chapter 3 – Security Testing | Completed |
| 12 | Include system reliability testing procedures. | Implement and evaluate an offline data storage and synchronization mechanism during network interruptions. | Revised Chapter 3 – Reliability Testing | Completed |
| 13 | Improve the organization of the system architecture. | Redesign the architecture using layered components consisting of Device, Network, Transport, Application, Database, and Monitoring layers. | Revised Chapter 4 – System Architecture | Completed |
| 14 | Strengthen the explanation of the security architecture. | Expand the security architecture by defining device authentication, network security, transport security, application security, database security, and monitoring mechanisms. | Revised Chapter 4 – Security Architecture | Completed |
| 15 | Add a security threat model. | Develop a STRIDE-based threat model with corresponding mitigation strategies for each identified threat. | Revised Chapter 4 – Threat Model | Completed |
| 16 | Ensure consistency throughout all chapters. | Review and align the title, objectives, methodology, implementation, evaluation, and terminology throughout the manuscript. | Updated Final Manuscript | Completed |
| 17 | Remove redundant and unnecessary citations. | Review all chapters and retain only relevant, credible, and consistent references following APA 7th Edition. | Updated References | Completed |
| 18 | Revise the project title for consistency. | Update the project title across all chapters to L-SIAMS: A Local IoT-Based Multi-Layer Secure Attendance Monitoring System with RFID and Biometric Authentication. | Updated Manuscript | Completed |
| 19 | Correct grammatical errors and maintain consistent tense usage. | Proofread the entire manuscript and revise grammar, sentence construction, and tense consistency. | Updated Manuscript | Completed |
| 20 | Include database layer security in the security architecture. | Modify the security architecture diagram to include the database security layer and corresponding controls. | Revised Security Architecture Diagram | Completed |
| 21 | Use a recognized vulnerability severity classification. | Integrate the Common Vulnerability Scoring System (CVSS) to classify security vulnerabilities. | Revised Chapter 3 and Chapter 4 | Completed |
| 22 | Complete and standardize all references. | Review and update all citations and references to comply with APA 7th Edition formatting requirements. | Final Reference List | Completed |

ACTIVITY 2

Project Scope Validation

Purpose

To verify that the approved project remains feasible and aligned with client requirements.

Procedure

- Review Chapter 1 and Chapter 3.

- Verify all objectives.

- Review scope and limitations.

- Identify any requested modifications.

- Complete Form 2.

FORM 2

PROJECT SCOPE VALIDATION FORM

Instructions

Check whether each component remains valid.

- Objectives Validation

| Objective | Still Applicable? | Remarks |
| --- | --- | --- |
| Design and implement an IoT-based attendance monitoring system using RFID and biometric fingerprint authentication for classroom-level attendance recording. | Yes | Remains aligned with the approved project title and addresses the identified attendance monitoring issues. |
| Develop a locally hosted web-based system for user management, attendance recording, report generation, and centralized database management. | Yes | Still applicable and consistent with the approved system architecture and client requirements. |
| Implement multi-layer security mechanisms including authentication, access control, encrypted communication, network security, and audit logging. | Yes | Supports the BSIT – Network Security specialization and remains one of the project's primary objectives. |
| Evaluate the developed system using ISO/IEC 25010 and ISO/IEC 27001 guided by the CIA Triad through performance, usability, reliability, and security testing. | Yes | Evaluation methodology remains unchanged and will be used during the testing phase. |

B. Requirements Validation

| Requirement | Validated | Remarks |
| --- | --- | --- |
| Functional Requirements | ☑ | All required modules remain applicable, including RFID attendance, fingerprint authentication, user management, attendance reports, audit logs, and dashboard monitoring. |
| Non-Functional Requirements | ☑ | Performance, reliability, security, maintainability, and usability requirements remain consistent with the approved proposal. |
| User Requirements | ☑ | Requirements gathered from Top Achievers Private School Inc. remain valid and no additional user requirements have been identified. |
| Hardware Requirements | ☑ | ESP32, MFRC522 RFID Reader, R307 Fingerprint Sensor, RFID Cards, Wi-Fi Router, Local Server, and Client Computers remain the required hardware components. |
| Software Requirements | ☑ | PHP, MySQL, HTML, CSS, JavaScript, Bootstrap, Visual Studio Code, XAMPP, GitHub, and Postman remain the planned software development tools. |

C. Scope Changes

List proposed modifications.

| Proposed Change | Reason | Adviser Approval |
| --- | --- | --- |
| Strengthened the implementation of multi-layer security mechanisms including API Key authentication, HTTPS/TLS encryption, Role-Based Access Control (RBAC), audit logging, and firewall configuration. | To improve the security architecture and better align the project with the BSIT – Network Security specialization. | Pending |
| Expanded the security testing methodology by incorporating Wireshark, Nmap, Metasploit, and CVSS-based vulnerability assessment. | To provide measurable and standardized security evaluation during system testing. | Pending |
| Enhanced the system architecture by introducing six security layers (Device, Network, Transport, Application, Database, and Monitoring Layer). | To improve the overall system organization, security, and maintainability based on panel recommendations. | Pending |

\

ACTIVITY 3

Work Breakdown Structure Development

Purpose

To organize all project activities and distribute responsibilities among team members.

Procedure

- List all tasks needed to complete the project.

- Group similar tasks together.

- Assign responsible members.

- Estimate completion dates.

- Complete Form 3.

FORM 3

WORK BREAKDOWN STRUCTURE (WBS)

Instructions

Break down project activities into smaller work packages.

| Major Deliverable | Task | Assigned Member | Due Week |
| --- | --- | --- | --- |
| Project Planning | Review project requirements, finalize project scope, assign team responsibilities, prepare project timeline, and conduct adviser consultation | Entire Team | Week 1 |
| System Design | Design the system architecture, database structure, user interface, and security architecture | Ched Nikko P. Pangilinan, Joshkirby Tyler M. Bote | Week 3 |
| Back-End & Database Development | Develop the MySQL database, authentication module, attendance module, reports module, and administrator dashboard | Ched Nikko P. Pangilinan | Week 8 |
| Front-End Development | Develop the responsive user interface, dashboard interface, and integrate the frontend with the backend | Joshkirby Tyler M. Bote | Week 9 |
| IoT Hardware Integration | Configure the ESP32, integrate the RFID reader and fingerprint sensor, and test hardware communication | Naph Yvan P. Villamar | Week 11 |
| Network Security Implementation | Configure Role-Based Access Control (RBAC), implement API authentication, HTTPS/TLS, audit logging, and conduct vulnerability assessment | Joshkirby Tyler M. Bote | Week 12 |
| System Testing | Conduct functional testing, integration testing, performance testing, security testing, and User Acceptance Testing (UAT) | Entire Team | Week 14 |
| Documentation | Update the capstone manuscript, prepare the user manual, technical documentation, presentation materials, and perform final proofreading | Entire Team | Week 17 |
| Deployment and Evaluation | Deploy the system, conduct client demonstration, collect evaluation results, apply final revisions, and prepare for the final defense | Entire Team | Week 18 |

Team Verification

All members must sign below:

- Ched Nikko P. Panglinan

- Naph Yvan P. Villamar

- Joshkirby Tyler M. Bote

ACTIVITY 4

Gantt Chart Preparation

Purpose

To establish a semester-long implementation schedule.

Procedure

- Use the completed WBS.

- Identify project milestones.

- Assign target weeks.

- Prepare the schedule.

- Complete Form 4.

FORM 4

GANTT CHART SUBMISSION FORM

Instructions

Indicate when each task will be performed.

| Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Planning | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Requirements Gathering | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| System Design |  | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Database Development |  |  | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Back-End Development |  |  |  | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |  |
| Front-End Development |  |  |  |  | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |
| IoT Hardware Integration |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |
| Network Security Implementation |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ |  |  |  |  |  |  |
| System Integration |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |  |  |  |
| Functional Testing |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |  |  |
| Performance & Security Testing |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |  |
| User Acceptance Testing (UAT) |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |
| System Deployment |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |
| Documentation | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |
| Final Evaluation & Defense Preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ |

Milestone Schedule

| Milestone | Target Week |
| --- | --- |
| Alpha Version | Week 8 |
| Prototype Presentation | Week 9 |
| Beta Version | Week 12 |
| Agency Immersion | Week 13 |
| Deployment | Week 16 |
| Evaluation | Week 17 |
| Mock Defense | Week 17 |
| Final Defense | Week 18 |

ACTIVITY 5

Development Planning

Purpose

To prepare the overall implementation strategy.

Procedure

- Determine development methodology.

- Identify technologies.

- Assign project roles.

- Identify risks.

- Complete Form 5.

FORM 5

PROJECT DEVELOPMENT PLAN

A. Team Roles

| Team Member | Role | Responsibilities |
| --- | --- | --- |
| Ched Nikko P. Pangilinan | Team Leader / Back-End Developer | Leads the project, develops the backend modules, designs and manages the database, oversees project progress, and prepares technical documentation. |
| Joshkirby Tyler M. Bote | Front-End Developer / Network Security | Develops the user interface, integrates frontend components, implements security features (RBAC, HTTPS/TLS, API authentication, audit logging), and assists in documentation. |
| Naph Yvan P. Villamar | IoT Hardware Developer / QA Tester | Integrates the ESP32, RFID reader, and fingerprint sensor, performs hardware testing, system integration, quality assurance, and troubleshooting. |

B. Development Methodology

Iterative a software development approach where a system is developed step by step through repeated cycles or iterations.e

C. Development Tools

| Category | Tool |
| --- | --- |
| Programming Language | PHP, JavaScript, HTML, CSS |
| Framework | Bootstrap |
| Database | MySQL |
| IDE | Visual Studio Code |
| Repository | GitHub (L-SIAMS Repository) |

D. Risk Management Plan

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Hardware integration issues (ESP32, RFID, Fingerprint Sensor) | Medium | High | Perform early hardware testing, verify component compatibility, and maintain backup hardware if available. |
| Development delays | Medium | High | Follow the project timeline, assign responsibilities clearly, and conduct weekly progress meetings. |
| Data loss or source code corruption | Low | High | Regularly back up the database and source code using GitHub and external storage. |
| Security vulnerabilities | Medium | High | Conduct security testing, implement RBAC, HTTPS/TLS, API authentication, and audit logging. |

E. Communication Plan

| Activity | Schedule |
| --- | --- |
| Team Meeting | Every other day or as needed |
| Adviser Consultation | Every week or if needed |
| Client Coordination | After every completed milestone or whenever feedback is required |

ACTIVITY 6

Repository Setup

Purpose

To establish version control and project collaboration mechanisms.

Procedure

- Create repository.

- Create project folder structure.

- Add all members.

- Commit initial files.

- Complete Form 6.

FORM 6

REPOSITORY SETUP REPORT

Repository Information

Repository Name:  LSIAMS

Repository URL: https://github.com/Joshhkopo/LSIAMS

Member Access

| Member | Access Granted |
| --- | --- |
| Ched Nikko P. Pangilinan | Yes |
| Joshkirby Tyler M. Bote | Yes |
| Naph Yvan P. Villamar | Yes |

Required Screenshots

Attach:

□ Repository Homepage

□ Team Members

□ Folder Structure

□ Initial Commit

Repository Structure

List folders created.

| Folder Name | Purpose |
| --- | --- |

| API.md | Contains the project's API documentation, including endpoints and usage instructions. |
| --- | --- |

| AttendanceService.php | Handles attendance-related functions and business logic. |
| --- | --- |

| BackupService.php | Manages database and system backup operations. |
| --- | --- |

| DEPLOYMENT.md | Provides instructions for deploying the application. |
| --- | --- |

| DashboardService.php | Handles dashboard data processing and related services. |
| --- | --- |

| DeviceService.php | Manages device-related operations and functionality. |
| --- | --- |

| README.md | Provides an overview of the project, installation steps, and usage information. |
| --- | --- |

| ReportService.php | Generates and manages reports within the system. |
| --- | --- |

| SECURITY.md | Documents the project's security policies and best practices. |
| --- | --- |

| ScheduleService.php | Handles scheduling and timetable-related operations. |
| --- | --- |

| backendddd/ | Contains the server-side source code, business logic, and backend components. |
| --- | --- |

| config.php | Stores application configuration settings. |
| --- | --- |

| cron.php | Executes scheduled or automated background tasks. |
| --- | --- |

| database.php | Establishes and manages the database connection. |
| --- | --- |

| dev-router.php | Provides routing configuration for the development environment. |
| --- | --- |

| docs/ | Stores project documentation and technical references. |
| --- | --- |

| fetch-vendor-assets.sh | Shell script used to download or update third-party/vendor assets. |
| --- | --- |

| frontendhtml/ | Contains the client-side interface, including HTML, CSS, JavaScript, and other front-end resources. |
| --- | --- |

ACTIVITY 7

Adviser Consultation

Purpose

To validate project readiness before development starts.

Procedure

- Present all Week 1 outputs.

- Discuss project schedule.

- Discuss risks and responsibilities.

- Record adviser recommendations.

- Complete Form 7.

FORM 7

ADVISER CONSULTATION RECORD

| Date | Topics Discussed | Adviser Recommendations | Action Items |
| --- | --- | --- | --- |

Consultation Checklist

| Item | Discussed |
| --- | --- |
| Project Scope | □ |
| Timeline | □ |
| Team Responsibilities | □ |
| Development Tools | □ |
| Risks | □ |
| Repository Setup | □ |

Adviser Approval

Adviser Name: Jesusimo L. Dioses Jr., D.Eng.

Signature:

Date: August _,2026